## Slide 1: UX Tools
Progress Report – Current Status

## Slide 2
UX Profiler
UX Index
UX Integration
UX Framework
UX Madness
Theoretical background
Internal Report 28/04
Preliminary
UX Framework
Academic Paper
Refinement of
UX Framework
Final
UX Framework
UX Interviews
Analysis of
Interviews
Dissemination
of Results
Selection of
Pilot Project
Interview
PP members
Tool
adaptation
Testing and
implementation
Theoretical background
Tentative
Process Model
First Simulation
Refinement
of ideas
Stakeholder
Workshop
Final version
Theoretical Background
Preliminary
Process Steps
Tool
Development
Workshop
with NRC
Refined
UXM
Pilot Test
Application
In PD Project
Theoretical Background
Preliminary
Process Steps
Questionnaire
Concept
Refined
Questionnaire
Pilot Test
With LinkedUI
Analysis and
Refinement

## Slide 3: Current Progress - UX Integration
Interviews
  Decision-making structure
  Methods
  Guidelines
  Opinions
  Etc.
Analysis of results
Dissemination of results
  UX Interview Report (27.04.2010)
  Report to Marko Ahtisaari (28.04.2010)
  Presentation of results at Nokia’s Xperience days (04.05.2010)
Determining UX Tools role in relation with Nokia’s product development environment

## Slide 4: Current Progress - UX Framework
Literature Review
Integration of UX Interviews findings
UX Framework theoretical background (Report 28.05.2010)
Dissemination of preliminary UX Framework

## Slide 5: Current Progress – UX Profiler
Theoretical background (80%)
Tentative process model
  Workshop with multi-disciplinary participants
  Inputs and outputs
First simulation
Refinement ideas

## Slide 6: Current Progress – UX Madness
Theoretical Background
Preliminary Process Model
Identification of UX Madness Tools application area (based on interviews)
Preliminary studies on UX Madness Tools
  Selection of Stimuli
  Assessment of Stimuli (in cooperation with UX Profiler)
    Testing of Stimuli in UX Profiler workshop
Refinement of original ideas – selection approach

## Slide 7: Current Progress – UX Index
Preliminary questionnaires
Refinement of questionnaire with NRC
Pilot test with Linked UI
Two different questionnaires
  Short (UX Score)
  Longer

## Slide 8: UX Tools
Progress Report – Next Steps

## Slide 9: UX Integration – Next Steps
Coming up with a suitable Pilot Project
Pilot Project personnel interviews
Adapt tools to comply with project environment
Testing and taking tools into action

## Slide 10: UX Framework – Next Steps
Academic paper on UX Framework
  Integration of Interview results as basis for UX Framework
Continuous refinement based on results

## Slide 11: UX Profiler – Next Steps
Interviews (in UX Integration)
  Finding out available user information
  Goals, needs, possibilities of Pilot project personnel
  Designer premises
Getting familiar with the Pilot Project environment
Refining UXP
Pilot/Simulation in a workshop
Refining UXP
Workshop with real stakeholders
Creating final version

## Slide 12: UX Madness – Next Steps
Interviews with UX Designers in Nokia (see UX Integration)
  Results: Adjusting UX Madness output format
Intensive collaboration (ca. 3 days with NRC)
  Defining UX Madness tool and Process for Pilot Study
  Testing UX Madness in friendly environment :)
  Refining UX Madness tool
Applying UX Madness tool in Pilot Study in conjunction with UX Profiler
Analyzing Results from Pilot Study in collaboration with Pilot Project Stakeholders
Refining UX Madness Tool and Process
Application in real project
Development of a “streamlined” UX Madness tool for online evaluation

## Slide 13: UX Index – Next Steps
Analysis of Results from LinkedUI study
Testing & Refinement
Final version

## Slide 14: UX Definition – Next Steps
“Humans live in their contexts* and act on different motivations. These activities are events that include using of some system. Humans transform into users when interacting with a system. User experience is the “part” of the experience that is attributed by the user to the use of the system. These events change the context and motivations of the user/human.”
* socio-, psycho-, physio-, ...