UX-Tools | Project Plan | 05.01.2010 | Draft 0.4 | Turkka Keinonen

Document owner: Lutz Gegner

User eXperience Tools (UX-Tools)

Nokia Research Center & Aalto University

Overview

User experience (UX) has replaced usability as a framework for user centred design of interactive products especially in consumer products and the service sector. However, UX is conceptually vague and difficult to apply as a New Product Design (NPD) evaluation and management approach.

The UX-Tools project aims at creating a set of tools and methods to assist companies in integrating UX into their product development processes.

The tools and methods include a UX-Profiler for identifying and defining UX targets, UX-Madness for diagnostic evaluation and development and UX-Index for quantitative evaluation.

The UX-Tools project is related to the research area “User needs and behaviours in the mobile domain” by supporting user and stakeholder centred design of mobile internet services, mobile generated content and mobile interaction solutions.

@@@ the longer background from my earlier version could be added here (unless someone has written a better one @@@

Project goal

The project goal is the creation of a framework and a set of methods and tools for user experience management in different phases of the product development process. UX has to be interpreted and compromised in the context of a Business and R&D management approach to ensure flexibility and relevance in decision making.

Therefore UX needs to be conceptualized by defining its relationships with usability, technology acceptance, attitude, satisfaction, preference and value. UX has to be integrated in order to support Design requirement management throughout NPD: from goal definition to post launch customer studies.

Participants and contact details

| Nokia Research Center: | Virpi Roto | 050 4836631 | virpi.roto@nokia.com |
| --- | --- | --- | --- |
|  | Mika Rautava | 050 4836326 | mika.rautava@nokia.com |
|  | Elina Ollila | 050 4821630 | elina.ollila@nokia.com |
| Aalto University: | Turkka Keinonen | 050 5723133 | turkka.keinonen@taik.fi |
|  | Jaakko Aspara | 050 5468891 | jaakko.aspara@hse.fi |
|  | Lutz Gegner | 046 8870986 | lutz.gegner@taik.fi |
|  | Marko Nieminen | 050 3684763 / 09 47023973 | marko.nieminen@tkk.fi |
|  | Mikael Runonen | 050 4365727 | mikael.runonen@tkk.fi |

Responsible heads of the project

Nokia Program Manager: Virpi Roto; Aalto Program Manager: Turkka Keinonen

Work packages

The project is divided into the following six main objectives, and correspondingly work packages

1. UX Framework

1. UX Framework

Task lead: T.K. and L.G.

The main deliverable of UX Framework is to consolidate and cluster the dimensions of UX based on existing literature. The sub-tasks for the UX Framework include:

Sub-task 1. Identification of UX-dimensions based on parallel theories and frameworks in interaction design, information system management and consumer behaviour literature.

    - deliverable: List of theories and frameworks from existing literature. @@@ list is not enough but we need to understand. a) what they aim at measuring, b) which is the theoretical landscape to which they belong, c) which are the (simplifying) assumptions that the models are based on, d) how are the dimensions operationalized, e) what is the scope of application for the models, f) how are they related to each others, g) other relevant issues @@@

    - activities:

  - Review and analysis of existing literature/theory.

  - Synthesis of existing literature/theory into a set of dimensions.

Sub-task 2. Identification of limitations of UX-dimensions in a business and R&D context

    - deliverable: Affinity diagrams and mind maps of UX-dimensions

    - activities:

2.1 Preparation and organization of expert interviews

2.2 Interviews with experts from NRC and operational units.

2.3 Analysis of expert interviews

@@@ this is what UX Integration should do @@@

Sub-task 3. Consolidation and clustering of collected UX-dimensions in a workshop @@@ actually we probably need several @@@

    - deliverable: Affinity diagrams and mind maps of UX-dimensions

    - activities:

  - Preparation of workshop.

  - Conducting and facilitating workshop

  - Analyzing workshop results

Sub-task 4. Development of a preliminary UX-Framework

    - deliverable: Preliminary UX-Framework.

    - Activities:

    - @@@ here we need to go to some kind of meta level of modeling. We need to decide about the criteria for a good framework, and here is when we need to link this task to UX integration. we need to think about the theoretical validity, the practical robustness and flexibility over projects and project phases, and some others @@@

  - Analysis and synthesis of the results of the preliminary sub-tasks

  - Development of preliminary UX Framework

  - Modification and refinement of UX Framework by workshop XX

Sub-task 5. Refinement of UX Framework

- deliverable: Final UX Framework as basis for tasks 2-5.

- activities:

  - Specification of UX-dimensions and translation into UX Framework

  - Presentation of results in workshop XX

2. UX Integration

...

3. UX Profiler

...

4. UX Madness

Task lead: T.K. and L.G.

The main deliverable of UX Madness is a specified process for diagnostic evaluation of UX in different stages of a product development process.

Sub-task 1. Identification of methods and techniques for stimulating and probing users.

- deliverable:  list of methods applied in diagnostic product evaluation @@@ as above: not just a list but an analysis @@@

- activities:

  - Review and analysis of existing literature/theory

  - Synthesis of existing literature into a set of methods and techniques

Sub-task 2. Outlining of methods and techniques in different stages of NPD (based on literature and workshops with Nokia usability experts and design teams). @@@ this should come from UX Integration @@@

- deliverable: List of methods and techniques for diagnostic evaluation.

- activities:

  - Expert interviews on diagnostic evaluation

  - Study of evaluation techniques within Nokia

  - Analysis and synthesis of findings

  - Modification and refinement of findings in Workshop XX.

Sub-task 3. Refinement and specification of preliminary UX Madness process

- deliverable: Preliminary UX Madness process model description

- activities:

  - Analysis and synthesis of preliminary process model steps and decision criteria.

  - Refinement and modification of

Sub-task 4. Pilot study and analysis of UX Madness on interactive prototypes.

- deliverable: Identification of strengths and weaknesses for further refinement

- activities:

  - Preparation of pilot study.

  - Conducting and facilitating pilot study on interactive prototypes at TaiK.

  - Analysis of results, modification and refinement of UX Madness in Workshop XX

Sub-task 5. Testing refined UX Madness with one or few product development projects.

    - deliverable: evaluation data and experiences concerning the applicability of UX Madness process model.

    - activities:

  - Identification and formatting of product and development stage specific process steps

  - Planning of the evaluation sessions with Nokia researchers

  - Conducting evaluation for the particular project by Nokia researchers

  - Evaluation and experiences obtained from testing UX Madness.

5. UX indeX (UXX)

The main deliverable of the UXX is a process model that specifies how a firm may develop a quantitative survey instrument to measure user experience with a prototype or final product/system. With respect to the survey instrument, the model specifies both fixed measurement items (that are used irrespective of the project/product under development) and product/project-specific measurement items, the formation of which is guided by the process model.

Sub-tasks for UXX include:

@@@ it is not mentioned here – and obviously up to the task leaders i.e. Jaakko to consider – but I feel that in NASA TLX structure there might be something that I would like to be seriously checked @@@

Sub-task 1. Identification of fixed measurement items (based on user experience literature and theory)

  - deliverable: list of fixed measurement items of the survey instrument to be

  - activities

1.1. Review and analysis of existing literature/theory by N.N. and J.A.

1.2  Synthesis of existing literature/theory into a set of measurement items by N.N. and J.A.

  - Modification, qualification, and selection of the measurement items by workshop XX

  - @@@ much of this actually should come from UX Framework @@@

Sub-task 2. Outlining of the types of product/project-specific measurement items (based on user experience literature and theory as well as workshops with usability experts)

  - deliverable: list of the types of product/project-specific measurement items

  - activities

  - Review and analysis of existing literature/theory by N.N. and J.A.

  - Identification of relevant types of product/project-specific measurement items items by by N.N. and J.A.

  - Modification, qualification, and selection of most important types of product/project-specific measurement items by workshop XX

- @@@ much of this should probably come UX Integration / UX profiler @@@

Sub-task 3. Specification of the process model 1: how the specific product/project-specific measurement items should be identified and formatted

  - deliverable: preliminary process model concerning the identification and formatting of the product/project-specific measurement items

  - activities

  - Analysis&synthesis of preliminary process model steps and decision criteria by N.N. and J.A.

  - Refinement of the preliminary process model stems and decision criteria by workshop XX

- @@@ much of this should probably come UX Integration / UX profiler @@@

Sub-task 4: Specification of the process model 2: how the survey should be conducted in a particular project (phases of sample selection and data gathering)

  - deliverable: preliminary process model concerning the conduct of the survey

  - activities

  - Analysis&synthesis of preliminary process model steps and decision criteria by N.N. and J.A.

  - Refinement of the preliminary process model stems and decision criteria by workshop XX

Sub-task 5: Testing of the process model with one or few product development projects

  - deliverable: evaluation data and experiences concerning the utilization of the process model

  - activities:

5.1  Identification and formatting of the product/project-specific measurement items for a particular Nokia project (based on the process model) by N.N., J.A., and Nokia researchers

5.2 Planning of the survey for the particular Nokia project (based on the process model) by N.N., J.A., and Nokia researchers

5.3 Conducting the survey for the particular Nokia project by Nokia researchers

  - Evaluating the data and experiences obtained from testing the survey ,by workshop XX

6. Administration and dissemination

...

Results and Deliverables:

The results and deliverables of the project can be divided into academic and industrial outcomes.

Academic:

Public dissemination of results as conference papers on international design research, HCI and UX forums. Inclusion of results in doctoral theses...

Industrial:

Process descriptions and demos of the individual workpackages. Organization of workshops for sharing the results with all stakeholders...

Milestones:

| M1 | 15.01.10 | Focused project plan |
| --- | --- | --- |
| M2 | 23.03.10 | Background study and conceptual framework of UX |
| M3 | 18.06.10 | Concepts of UX design and evaluation approaches |
| M4 | ~Sep. 2010 | Early prototypes. |
| M5 | ~Nov 2010 | Early pilot tests and feasibility study. |
| M6 | ~Feb 2011 | Phase 2 prototypes with study results. |
| M7 | ~Jun 2011 | Phase 3 prototypes with study results. |
| M8 | ~Sep 2011 | Phase 4 prototypes with study results. |
| M9 | ~Nov 2011 | Final deliverables from all tasks. |

Workshops:

Monthly workshops are organized for sharing and discussing the results of the research. To this point the workshops for the first half year of the project are:

| W1 | 07.01.10 | Project Plan Development |
| --- | --- | --- |
| W2 | 15.01.10 | Focused Project Plan (M 1) |
| W3 | 09.02.10 | Business context and R&D context |
| W4 | 23.03.10 | Background study and conceptual Framework (M 2) |
| W5 | 14.04.10 | Work package UX-Index |
| W6 | 13.05.10 | Work package UX-Profiler |
| W7 | 18.06.10 | Work package UX-Madness, Concepts of UX design and evaluation approaches (M 3) |